## Defect register
No. | Building | Level | Unit / area | Room | Description | Type | Classification | Raised by | Raised on | Photo | Assigned to | Cost to | Due | Work started | Status | Fixed on | Proof photo | Verified by | Closed on | Notes
214 | Block A | 3 | Apt 3.07 | Ensuite | Grout cracked along the shower hob, approx. 600 mm, water tracking under the hob on the shower side. Membrane suspect. | Defect | Waterproofing - membrane | K. Hartley (site manager) | 2026-04-21 | IMG_4471.jpg | Aqua Seal Waterproofing | Defect | 2026-04-24 | 2026-04-22 | Fixed - awaiting inspection | 2026-04-23 | IMG_4519.jpg |  |  | Hold tiler until verified.
215 | Block A | 3 | Apt 3.07 | Bedroom 2 | Door binds on the top hinge, will not close without lifting. Frame appears out of square at the head. | Defect | Carpentry - door hardware | K. Hartley (site manager) | 2026-04-21 | IMG_4473.jpg | Hanley Joinery | Defect | 2026-04-24 | 2026-04-22 | Closed | 2026-04-22 | IMG_4502.jpg | S. Okonkwo (QA) | 2026-04-23
216 | Block A | 3 | Landing | Stair 2 | Handrail bracket missing at the third fixing from the top. Rail flexes under load. | Incomplete works | Metalwork - balustrade | R. Adeyemi (employer's agent) | 2026-04-21 | IMG_4478.jpg | Precision Metalwork | Variation | 2026-04-28 |  | Assigned |  |  |  |  | Bracket was never on the drawing. Raised as a variation, not a defect.

## What each column is for
Column | What it is for
No. | Assigned once, never reused. Encodes nothing that can change.
Building | Structured location, part 1.
Level | Structured location, part 2.
Unit / area | Structured location, part 3.
Room | Structured location, part 4.
Description | Written for a stranger reading it in eleven months.
Type | Defect, Incomplete works, Warranty, Variation, Safety, Maintenance.
Classification | Trade and failure, from your own list.
Raised by | The person who reported it, not the person who typed it.
Raised on | Date logged.
Photo | Filename or link. Taken at capture, not later.
Assigned to | The trade or contractor doing the work.
Cost to | Who pays: Defect, Variation or Backcharge.
Due | Fix-by date.
Work started | Set on the first move out of Open. Never edited.
Status | Open, Assigned, In progress, Fixed - awaiting inspection, Closed, In dispute, Outstanding.
Fixed on | The trade's claim, with a photo.
Proof photo | Photo of the finished work. Required before Fixed.
Verified by | Someone who is not the trade.
Closed on | Date verified and closed.
Notes | Anything else. Never a substitute for the columns.
From issuesid.com/defect-register-template/ - the page explains the columns, the worked example, and where a spreadsheet stops being enough.