## DLP inspection
Ref | Area | Check | Result | Item type | Already notified | Defect no. | Photo | Checked by | Checked on | Notes
A1 | Walls, ceilings and floors | No new cracking at cornices, wall joints or above door and window heads | Fail | Defect | No | ABC-342 | IMG_7720.jpg | L. Nguyen (owner's rep) | 2026-10-06 | Crack along living-room cornice, approx. 1.8 m, opened over winter. Raised at the walk.
A2 | Walls, ceilings and floors | No nail pops or joint lines showing through paint
A3 | Walls, ceilings and floors | Floors free of new squeaks, cupping, lifting or gaps
A4 | Walls, ceilings and floors | Floor tiles sound; no new cracked or drummy tiles
A5 | Walls, ceilings and floors | Skirting and architraves still fixed and gap-free
B1 | Wet areas | No staining or bubbling on the ceiling below any bathroom, ensuite or laundry | Fail | Defect | Yes | ABC-311 | IMG_7714.jpg | L. Nguyen (owner's rep) | 2026-10-06 | Stain below ensuite reported by owner on QR card in month seven; larger than the August photo.
B2 | Wet areas | Silicone at shower, bath, vanity and floor junctions intact and adhered
B3 | Wet areas | Grout intact; no cracking at the shower hob or niche
B4 | Wet areas | Floor falls to waste; no ponding after a water test
B5 | Wet areas | Shower screen sealed; dry outside the screen after a test
B6 | Wet areas | No leak under the vanity, sink or laundry tub after running
B7 | Wet areas | Exhaust fans run and vent outside
C1 | Balconies, roof and drainage | Balcony falls to drain; no ponding after a water test | Fail | Maintenance | No |  | IMG_7716.jpg | L. Nguyen (owner's rep) | 2026-10-06 | Ponding after 10 min water test; grate packed with leaves, runs clear once lifted. Before and after photos.
C2 | Balconies, roof and drainage | Balcony door threshold dry after a test
C3 | Balconies, roof and drainage | No staining or efflorescence on the soffit or wall below the balcony
C4 | Balconies, roof and drainage | Gutters and downpipes discharge; joints not leaking
C5 | Balconies, roof and drainage | No water staining on ceilings below the roof or flashings
C6 | Balconies, roof and drainage | Ground falls away from the building; no ponding against walls after rain
D1 | Windows and doors | Windows open, close and lock smoothly
D2 | Windows and doors | Window seals and sills intact; no water marks on reveals
D3 | Windows and doors | Internal doors close and latch without binding
D4 | Windows and doors | Entry and external doors seal; no daylight at the threshold
D5 | Windows and doors | Door and window hardware tight and working
D6 | Windows and doors | Garage door operates; manual release works
E1 | Services | Hot water reaches temperature at the furthest outlet
E2 | Services | Air conditioning heats and cools; condensate drains away from the building
E3 | Services | Smoke alarms tested and interconnected
E4 | Services | RCDs test and reset
E5 | Services | Taps and mixers free of drips at rest
E6 | Services | Toilets flush fully and stop
F1 | Finishes and joinery | Paint free of peeling, blistering or water marks
F2 | Finishes and joinery | Cabinet doors and drawers aligned and closing
F3 | Finishes and joinery | Benchtop joins sealed and flush
F4 | Finishes and joinery | Carpet seams tight; no rippling
G1 | External | Render, cladding and brickwork free of new cracks
G2 | External | External sealant joints intact around windows and penetrations
G3 | External | Paving and driveway free of new cracking or sinking
G4 | External | Fences, gates and letterbox fixed and operating

## What each column is for
Column | What it is for
Ref | Area letter and item number. Stays the same on every unit so defects can quote it.
Area | The part of the building the check belongs to.
Check | One observable thing, phrased so Yes means it passes.
Result | Pass, Fail or N/A. A Fail becomes an item on the register at the walk.
Item type | Defect, Maintenance or Wear. Decide it at the walk, with the photo.
Already notified | Yes if the item was reported during the period and is already on the register.
Defect no. | The number of the item on your register, new or existing.
Photo | Filename of the photo taken at the check.
Checked by | Who answered it, and for which side.
Checked on | Date answered.
Notes | The water test, what the owner described, what the trade said.
From issuesid.com/dlp-inspection-checklist/ - the page explains the checks, defect or maintenance, and where the end-of-DLP walk goes wrong.