## ITP
Item | Stage | Inspection or test | Acceptance criteria | Reference | Frequency | Record | Subcontractor | Builder | Engineer / Superintendent | Signed by | Date | Notes
1 | Set-out | Survey check of slab edge, penetrations and set-downs | Within +/- 10 mm of drawing | A-201 rev C; survey control sheet | Each pour | Survey report | H | W | S | L. Chen (surveyor) | 2026-05-11
2 | Formwork | Formwork line, level, cleanliness and release agent | Level within +/- 5 mm; no debris; agent applied | AS 3610; S-001 rev B general notes | Each pour | Pre-pour checklist item 2 | H | W |  | M. Reyes | 2026-05-12
3 | Reinforcement | Bar size, spacing, laps, chairs and cover | As S-201 rev C; cover 50 mm bottom; laps per schedule | S-201 rev C note 7; AS 3600 | Each pour | Pre-pour checklist item 3; cover meter log | H | H | H | D. Marsh (structural engineer) | 2026-05-13 | Hold released after chair replacement, NCR-031.
4 | Embedments and services | Conduits, penetrations, cast-in plates located and fixed | As services drawings; fixed against movement | E-301 rev A; H-201 rev B | Each pour | Pre-pour checklist item 4 | H | W |  | M. Reyes | 2026-05-13
5 | Pre-pour release | All hold points above released; pump and crew confirmed | Items 1 to 4 signed | ITP-CON-03 | Each pour | Pre-pour checklist | H | H | H | D. Marsh (structural engineer) | 2026-05-14
6 | Concrete delivery | Docket check: mix, slump, time from batching | Mix as specified; slump within +/- 15 mm; placed within 90 min | Spec 03300 cl 2.4; AS 1379 | Each truck | Delivery dockets; slump test record | S | W |  | M. Reyes | 2026-05-14
7 | Placement and finish | Compaction, level, finish and tolerances | Surface within 3 mm under 3 m straightedge | Spec 03300 cl 3.6 | Each pour | Pour record | S | W |  | M. Reyes | 2026-05-14
8 | Curing and stripping | Curing method applied; strip no earlier than specified | Cured 7 days; strip at 70% f'c per engineer | Spec 03300 cl 3.8; S-001 rev B | Each pour | Curing log; cylinder results | S | W | W | M. Reyes | 2026-05-21

## What each column is for
Column | What it is for
Item | Sequence number within the activity.
Stage | The step in the work this check sits at.
Inspection or test | What is inspected or tested, and how.
Acceptance criteria | The number, tolerance or condition that passes.
Reference | The drawing, specification clause or standard that sets the criterion, with revision.
Frequency | Every pour, every 50 m3, each delivery, once per level.
Record | The form, checklist, certificate or docket kept as evidence.
Subcontractor | H, W or S for the party doing the work.
Builder | H, W or S for the head contractor.
Engineer / Superintendent | H, W or S for the designer or client's representative.
Signed by | Who released or witnessed it, by name.
Date | Date signed.
Notes | Anything else. Never a substitute for the columns.
From issuesid.com/itp-template/ - the page explains the columns, the H/W/S codes, a worked slab ITP, and where an ITP on paper breaks.