## PC inspection
Ref | Area | Check | Result | Hold point | Defect no. | Photo | Checked by | Checked on | Notes
A1 | Entry | Front door closes and latches without lifting or forcing |  | No
A2 | Entry | Lockset and all keys operate; keys tagged to the unit |  | No
A3 | Entry | Door stop fitted; door does not strike a wall or fitting |  | No
A4 | Entry | Intercom or access control rings and releases |  | No
A5 | Entry | Entry floor finish level, no lippage or cracked tiles |  | No
B1 | Living and dining | Walls free of marks, patching shadows and nail pops |  | No
B2 | Living and dining | Cornice continuous; no gaps or cracked joins |  | No
B3 | Living and dining | Skirting fixed, gaps caulked and painted |  | No
B4 | Living and dining | Windows open, close and lock; weep holes clear |  | No
B5 | Living and dining | Window reveals and sills sealed; no daylight at frames |  | No
B6 | Living and dining | Floor finish free of scratches, gaps and squeaks |  | No
B7 | Living and dining | Every GPO and switch tested live |  | No
B8 | Living and dining | TV and data points terminated and live |  | No
B9 | Living and dining | Air conditioning runs on heat and cool; condensate drains |  | No
B10 | Living and dining | Blinds or curtains fitted and operate |  | No
C1 | Kitchen | Benchtop joins sealed and flush |  | No
C2 | Kitchen | Cupboard doors aligned; handles fixed |  | No
C3 | Kitchen | Drawers run to full extension and self-close |  | No
C4 | Kitchen | Splashback silicone continuous at bench and wall |  | No
C5 | Kitchen | Sink drains freely; no leak under bench after running |  | No
C6 | Kitchen | Mixer operates; no drip at rest |  | No
C7 | Kitchen | Dishwasher connected, cycles, no leak |  | No
C8 | Kitchen | Rangehood runs and vents; filter fitted |  | No
C9 | Kitchen | Cooktop and oven operate on every element |  | No
C10 | Kitchen | GPOs above bench live and clear of the splashback edge |  | No
D1 | Bathroom and ensuite | Waterproofing certificate sighted for this wet area |  | Yes
D2 | Bathroom and ensuite | Tiles level, no cracks, no drummy tiles |  | No
D3 | Bathroom and ensuite | Grout complete and consistent; no missing runs | Fail | No | ABC-214 | IMG_4471.jpg | J. Okafor | 2026-09-22 | Grout missing, shower niche, left return, 300 mm run.
D4 | Bathroom and ensuite | Silicone continuous at wall-to-floor and wall-to-wall junctions |  | No
D5 | Bathroom and ensuite | Floor falls to waste; no ponding after water test | Pass | Yes |  | IMG_4473.jpg | J. Okafor | 2026-09-22 | Water test 10 min, drained in 40 s.
D6 | Bathroom and ensuite | Shower screen sealed; no leak outside the screen after test |  | No
D7 | Bathroom and ensuite | Vanity drains; no leak under after running |  | No
D8 | Bathroom and ensuite | Toilet flushes fully and stops; no running cistern |  | No
D9 | Bathroom and ensuite | Exhaust fan runs and vents |  | No
D10 | Bathroom and ensuite | Mirror, rails and accessories fixed and level |  | No
E1 | Bedrooms | Door closes and latches; no rub on carpet |  | No
E2 | Bedrooms | Robe doors aligned and run freely |  | No
E3 | Bedrooms | Robe shelving and rail fixed and level |  | No
E4 | Bedrooms | Carpet seams tight; edges tucked |  | No
E5 | Bedrooms | Windows open, close and lock |  | No
F1 | Laundry | Taps operate; no drip at rest |  | No
F2 | Laundry | Tub drains freely; no leak under |  | No
F3 | Laundry | Washing machine and dryer points live |  | No
F4 | Laundry | Floor waste present and clear |  | No
F5 | Laundry | External door seals; no daylight at threshold |  | No
G1 | Balcony and terrace | Falls to drain; no ponding after water test |  | No
G2 | Balcony and terrace | Balustrade fixed and secure under load |  | Yes
G3 | Balcony and terrace | Door threshold sealed; no water entry after test |  | No
G4 | Balcony and terrace | Tiles or decking sound; no drummy or loose units |  | No
H1 | Services | Smoke alarm tested and interconnected | Pass | Yes |  | IMG_4480.jpg | J. Okafor | 2026-09-22 | Both alarms sounded; interconnect confirmed.
H2 | Services | Switchboard labelled; RCDs test and reset |  | No
H3 | Services | Hot water unit runs; temperature at the furthest outlet |  | No
H4 | Services | Water meter and isolation valve located and labelled |  | No
H5 | Services | Gas isolation located and labelled |  | No
H6 | Services | NBN or fibre termination fitted and live |  | No
I1 | External and common | Unit number fitted at door and letterbox |  | No
I2 | External and common | Letterbox key operates |  | No
I3 | External and common | Garage door remote and manual release operate |  | No
I4 | External and common | Storage cage door locks; number fitted |  | No

## What each column is for
Column | What it is for
Ref | Area letter and item number. Stays the same on every unit so defects can quote it.
Area | The room or system the check belongs to.
Check | One observable thing, phrased so Yes means it passes.
Result | Pass, Fail or N/A. A Fail raises a defect; record its number in the next column.
Hold point | Yes for the checks the unit cannot be signed off without.
Defect no. | The number of the defect raised for a Fail, on your register.
Photo | Filename of the photo taken at the check, for a Fail or a hold point.
Checked by | Who answered it.
Checked on | Date answered.
Notes | Anything else. Never a substitute for the Result column.
From issuesid.com/pre-completion-inspection-checklist/ - the page explains the checks, the hold points and where a paper checklist breaks.