## Snag list
No. | Level | Unit / area | Room | Item | Trade | Photo | Priority | Raised on | Raised by | Due | Status | Completed on | Proof photo | Verified by | Closed on | Notes
S-118 | 4 | 4.02 | Entry | Door catches on carpet at the latch side; 2 mm carpet over spec, see flooring | Flooring | IMG_5102.jpg | Standard | 2026-09-16 | T. Moana | 2026-09-19 | Closed | 2026-09-18 | IMG_5188.jpg | T. Moana | 2026-09-19 | Disputed by carpenter 17 Sep; re-issued to flooring, cost to carpet supplier.
S-119 | 4 | 4.02 | Ensuite | Grout missing, shower niche, left return, 300 mm run | Tiler | IMG_5103.jpg | Standard | 2026-09-16 | T. Moana | 2026-09-26 | Completed by trade | 2026-09-24 | IMG_5201.jpg
S-120 | 4 | L4 corridor | Corridor | Handrail bracket loose at stair 2 landing; moves under hand load | Metalwork | IMG_5104.jpg | Safety | 2026-09-16 | T. Moana | 2026-09-16 | Closed | 2026-09-16 | IMG_5110.jpg | R. Doyle | 2026-09-16 | Fixed same day; fixings replaced.
S-121 | 4 | 4.05 | Kitchen | Rangehood not venting; duct disconnected above bulkhead | Mechanical | IMG_5105.jpg | High | 2026-09-16 | T. Moana | 2026-09-18 | Issued |  |  |  |  | Access through bulkhead panel; painter to make good after.

## What each column is for
Column | What it is for
No. | A permanent number, never reused.
Level | Floor or level.
Unit / area | Unit number, or the common area name.
Room | The room, from an agreed list.
Item | What is wrong, where on the thing, and how much of it.
Trade | Whose work it is.
Photo | Filename of the photo taken when it was found.
Priority | Safety, High or Standard.
Raised on | Date found.
Raised by | Who found it.
Due | Fix-by date, set when it is issued.
Status | Open, Issued, In progress, Completed by trade, Verified, Closed, Disputed.
Completed on | Date the trade said it was done.
Proof photo | Filename of the trade's photo of the finished work.
Verified by | Who checked the fix. Not the trade.
Closed on | Date verified and closed.
Notes | Anything else. Never a substitute for the columns.
From issuesid.com/snag-list-template/ - the page explains the columns, four worked snags, and where a snag list breaks.